## Master List
Item Number | Project Name | Lead | Goals | Requester | Expected Date of Completion | Percent Complete/Status | Cost/Necessary Resources | Priority | Comments/Related Strategic Plan Elements
Strategy/Communications
S1 | Reporting Mission Hours Compliance | M Jones DSO-IS | Improve compliance with reporting mission hours | DCO | 2015-08-31 | 10% | DSO-IS, DSO-PA | High | Messaging drafted for DCDRs in progress 31AUG14 by DSO-IS. S/P 4.A.2.Demonstrate value of Auxiliary to District.
S2
S3
S4
District Operations (Example Term)
O1 | NACON Courses | D Lawrence DSO-MT | Coordinate NACON Course Topics | T-DIR | 2015-07-31 | 10% | DIRAUX Funds DSO-MT | High | Started discussion with National Conference and T-DIR staff. DIRAUX will fund 3 members. S/P 4.A.2.h. Encourage training beyond the qualification and sustainment levels so that members can strive to become proficient in their activities.T-DIR
O2
O3
O4
HR/Staffing (Example Term)
H1 | Fill DSO-OP | J Jones DCAPT | Fill vacancy | DCO | 2014-08-31 | 10% | DCAPT | High | DSO-OP resigned 19AUG14. S/P 4.A.2.j. Cultivate leadership skills and succession management.
H2 | Awards | DCOS/DCAPT-S | Develop Awards for Staff | Internal | 2014-03-31 | 100% | T-DIR | High | Submit and complete awards for Dxx staff. Confirmed that awards have been processed. S/P 4.A.2.c. Encourage retention of existing members through mentoring, awards programs, and similar active efforts to let members know that their efforts are needed and appreciated.
H3
H4
Systems/Processes (Example Term)
P1
P2
P3
P4
| Dave Jones | DCO | Dxx Commodore
| Randy Lewis | DCOS | Dxx Chief of Staff
| Robert Franks | DCAPT-S | DCAPT-Support/Planning
| Matt Ryan | DCAPT-R | DCAPT-Response
| Jeff Parks | DCAPT-P | DCAPT-Prevention

## Strategic Plan Elements
Strategic Plan Elements Examples
S/P 4.A.2.e. Promote communication among all levels of the Auxiliary.
S/P 4.A.1.b.i. Promote Auxiliary District interaction with Coast Guard District and Sector leadership.
S/P 4.A.2.f. Promote the use of communication technology within the Auxiliary.
S/P 4.A.2.h. Encourage training beyond the qualification and sustainment levels so that members can strive to become proficient in their activities.
S/P 4.A.2.j. Cultivate leadership skills and succession management.
S/P 4.A.2.k. Ensure qualification requirements reflect the mission for which the member is being trained.
S/P 4.A.2.l. Streamline the currency maintenance process.
S/P 4.B.2.a. Establish a formal training program for staff to effectively fulfill their responsibilities in service to membership.